## Sheet1
|  |  | Updated on | 2017-02-17
Dep. | IT |  | Updated by | Võ Trường An
Attn. | An
LS project
# | Members | Start Date | End Date | Module | Function | Progress | Note
1 | An | 2017-02-17 | 2017-02-21 | Open Liberary | Front-end | 20%
| An | 2017-02-20 | 2017-03-02 | Open Liberary | Back-end: Create (Insert) : UI, BL, DB Test (Unit test, function test) | 10%
| An | 2017-02-20 | 2017-03-04 | Open Liberary | Back-end: Edit ( update ) : UI, BL, DB Test (Unit test, function test) | 5%
| An | 2017-02-20 | 2017-03-02 | Open Liberary | Back-end: Delete : UI, BL, DB Test (Unit test, function test) | 0%
| An | 2017-03-04 | 2017-03-06 | Galley | Front-end | 5%
| An | 2017-03-06 | 2017-03-15 | Galley | Back-end | 0%
2 | Phong | 2017-02-16 | 2017-02-18 | Login | Front-end | 50%
| Phong | 2017-02-18 | 2017-02-20 | Login | Back-end | 0%
| Phong | 2017-02-20 | 2017-03-10 | Class Management | Front-end | 0%
| Phong | 2017-02-20 | 2017-03-22 | Class Management | Back-end: Introduction: UI, BL, DB Test (Unit test, function test) | 0%
| Phong | 2017-02-22 | 2017-03-24 | Class Management | Back-end: Conspectus: UI, BL, DB Test (Unit test, function test) | 0%
| Phong | 2017-02-25 | 2017-02-27 | Class Management | Back-end: CheckAttendanceAndEnterPoints : UI, BL, DB Test (Unit test, function test) | 0%
| Phong | 2017-02-28 | 2017-03-01 | Class Management | Back-end: ClassListAndPoint : UI, BL, DB Test (Unit test, function test) | 0%
| Phong | 2017-03-02 | 2017-03-04 | Class Management | Back-end: Conspectus : UI, BL, DB Test (Unit test, function test) | 0%
| Phong | 2017-03-05 | 2017-03-07 | Class Management | Back-end: Discuss : UI, BL, DB Test (Unit test, function test) | 0%
| Phong | 2017-03-08 | 2017-03-10 | Class Management | Back-end: Notification : UI, BL, DB Test (Unit test, function test) | 0%
| Phong | 2017-03-10 | 2017-03-12 | Class Management | Back-end: LessonsAndReference : UI, BL, DB Test (Unit test, function test) | 0%
3 | Vân | 2017-02-16 | 2017-02-28 | Information management , Siteinfo | Front-end | 10%
|  |  |  | Siteinfo | Back-end(Siteinfo):Create (Insert) : UI, BL, DB Test (Unit test, function test) | 0%
[5 empty] | Back-end(Siteinfo ): Edit ( update ) : UI, BL, DB Test (Unit test, function test) | 0%
[5 empty] | Back-end(Siteinfo): Delete : UI, BL, DB Test (Unit test, function test) | 0%
|  |  |  | Information management | Back-end(Information management ):Create (Insert) : UI, BL, DB Test (Unit test, function test) | 0%
[5 empty] | Back-end(Information management ): Edit ( update ) : UI, BL, DB Test (Unit test, function test) | 0%
[5 empty] | Back-end(Information management ): Delete : UI, BL, DB Test (Unit test, function test) | 0%
4 | Ngân | 2017-02-16 | 2017-02-28 | News management , Management Member | Front-end | 25%
4 | Ngân | 2017-02-16 | 2017-02-28 | News management , Management Member | Back-end(News):Create (Insert) : UI, BL, DB Test (Unit test, function test) | 5%
4 | Ngân | 2017-02-16 | 2017-02-28 | News management , Management Member | Back-end(News): Edit ( update ) : UI, BL, DB Test (Unit test, function test) | 5%
4 | Ngân | 2017-02-16 | 2017-02-28 | News management , Management Member | Back-end(News): Delete : UI, BL, DB Test (Unit test, function test) | 0%
4 | Ngân | 2017-02-16 | 2017-02-28 | News management , Management Member | Back-end(Menbers):Create (Insert) : UI, BL, DB Test (Unit test, function test) | 0%
4 | Ngân | 2017-02-16 | 2017-02-28 | News management , Management Member | Back-end(Menbers): Edit ( update ) : UI, BL, DB Test (Unit test, function test) | 0%
4 | Ngân | 2017-02-16 | 2017-02-28 | News management , Management Member | Back-end(Menbers): Delete : UI, BL, DB Test (Unit test, function test) | 0%